## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## Content
SM Clone
Scrum Doc, Software Dev Project Summer 2022
Developers: Basil Omsha
Content
1) Product backlog
2) Tasks
3) Sprint planning meeting
3) Sprint Backlog -1
4) Sprint Backlog -2

## ProductBacklog
Product Backlog - Project Title
User Stroy | Story Point(s) | Priority
As an admin, I am able to log in. | 6 | 1
As an dmin, I am able to add, edit and remove profiles. | 6 | 1
As an admin, I am able to delete users pictures. | 6 | 1
As an admin, I am able to add, edit and remove users posts. | 6 | 1
As a user, I am able to register and become a registerd user. | 4 | 1
As a user, I am able to login. | 6 | 3
As a user, I am able to see a list of other registered users. | 2 | 3
As a user, I am able to write posts. | 4 | 1
As a user, I am able to edit my profile. | 4 | 1
As a user, I am able to upload profile picture. | 4 | 3
As a user, I am able to upload pictures to my posts. | 4 | 5
Aa a user, I am able to delet my profile. | 2 | 1
Priorities
1= Vital
3= important
5= The least important
2
6
10
4
8
Walk in a park
Veteran
Challenging
Medium
Hard
Story Points

## Tasks
User stories and their related tasks
User Stories | Tasks | Status | Status key
|  |  | Done |  | Undone
Plan the database and the necessary relationships
Admins are able to log in from a hidden link
As an admin, I am able to log in. | The login page esablishes a connection with the db and checks if the credentials are available in the db
If the username or password are wrong, inform the user with an error message
In process
Design an admin page UI
As an dmin, I am able to add, edit and remove profiles. | Connects to registered candidates db
Able to edit, select, inseret and drop the db info
Connects also to users db table
As an admin, I am able to delete users pictures. | Able to edit, select, inseret, and drop the db info
Connects to users db table
As an admin, I am able to add, edit and remove users posts. | Able to edit, select, inseret, and drop the db info
Create the signup page and a link to it in the login page
Connect to the database and save the new users there
As a user, I am able to register and become a registerd user.
Create a users login page
As a user, I am able to login and logout. | Add a form that connects to the database
servlets to login and out
Create a list of candidates in the voter page
As a user, I am able to see a list of other registered users.
Connect posts db table
As a user, I am able to write posts. | Create a new post in the db
Create a feeds page where users can write new posts
Connects to users db table
As a user, I am able to edit my profile. | Update users db table
Create "my Profile" page
Create and editing page with a correct form
Create an upload button in view my profile page
As a user, I am able to upload profile picture.
Pictures data saved to the psots db table
As a user, I am able to upload pictures to my posts.
Create a delete button
Connect to users db table and delete the profile basedon the ID
Aa a user, I am able to delet my profile.

## sprint_planning_meetings
Spring Planning | Participants
Sprint 1 Week25 | Basil | Column1 | Column2
Location | X |  |  | If physically present mark X
Date: 22.06.2022
Sprint 2 Week 26
Location | X
Date: 3.8.2022
Sprint 3 Week 27
Location
Date: 25.4.2022
Sprint 4 Week 28
Location
Date
Sprint 5 Week29
Location
Date
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## sprint_backlog_sprint1
Sprint Backlog : Sprint 1 22.06.22- 03.08.22
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 points | DAY 2 points | DAY 3 points | DAY 4 points | DAY 5 points
Create GitHub repository |  |  | Done
Make sure the environment works properly |  |  | Done
Plan the database and the necessary relationships | 3 |  | Done
Design the database |  |  | Done
Create the necessarry tables |  |  | Done
Define the relatioship between |  |  | Done
Defining Application architecture | 2 |  | Done
app: includes the client servlet "userClient" that sends and receives requests |  |  | Done
modle: includes data modles "User" to process the data received from the request |  |  | Done
rest: includes restFul services to call CRUD functions from dao class |  |  | Done
conn: includes a Connections class handles database connection with a connection pool |  |  | Done
dao: includes all the CRUD functions needed |  |  | Done
security: includes "securityUtils" class that hashes passwords and adds salt for extra security |  |  | Done
User Story #1: As a user, I am able to register and become a registerd user. | 4 |  | Done
Creating the main page with a signup an login form using html, js and css (index.html) |  |  | Done
Create a client servlet (userClient) to add a user, using rest services that call functions from dao class |  |  | Done
Add a rest function to call function from dao class |  |  | Done
Create a function to add a user to the data base in dao class |  |  | Done
Create a doa function to check for duplicate emails and return an error message for the user |  |  | Done
Create a function to show the a message once sign up is completed on main page. |  |  | Done
User Story #2: As a user, I am able to login. | 6 |  | In Process
User Story #3: As a user, I am able to edit my profile. | 4 |  | In Process
TOTAL | 19 |  |  | 0 | 0 | 0 | 0 | 0

## sprint_backlog_sprint2
Sprint Backlog : Sprint 2 03.08.22-
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #2: As a user, I am able to login and logout. | 6 |  | Done
Create a profile page for users to land on after sgining in using jsp, html, css nad js |  |  | Done
Navbar on the page sticks while scroling using window.onscroll function. |  |  | Done
Login servlet created uses post method |  |  | Done
Logout servlet creatred |  |  | Done
A servlet to show user info created |  |  | Done
logout servlet that invalidate sessions and redirects to login page |  |  | Done
User Story #3: As a user, I am able to edit my profile. | 4 |  | Done
rest service to update name that calls function from dao |  |  | Done
JS to refresh the page once update buttonis clicked or enter is pressed |  |  | Done
rest service to update email that calls function from dao |  |  | Done
rest service to update gender that calls function from dao |  |  | Done
rest service to update birthdate that calls function from dao |  |  | Done
rest service to update Password that calls function from dao also hidden behind a password |  |  | Done
User Story #4: As a user, I am able to delete my profile. |  |  | In process
rest service to delete accout calss a function from dao |  |  | In process
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0

## sprint_backlog_sprint3
Sprint Backlog : Sprint 3
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0